## Resumen
Filtro
product	TOL

Cantidad - bug_id	severidad
estado	fallo	mejora	Total Resultado
pendiente	9	1	10
postergado	12	7	19
resuelto	310	33	343
Total Resultado	331	41	372
Porcentaje de bugs de TOL por estado actual

## Agregado por aparición
Versión de aparición	fallo	mejora	Total	Días	Bugs/Día
1.1.0	10	2	12	329	0.04
1.1.1	153	16	169	273	0.62
1.1.2	72	11	83	237	0.35
1.1.3	56	7	63	182	0.35
1.1.4	14		14	59	0.24
1.1.5	26	5	31	195	0.16
Total Resultado	331	41	372	1274	0.29
Evolución de bugs de TOL nuevos por día

## Agregado por resolución
Cantidad - bug_id	severidad
Versión de resolución	fallo	mejora	Bugs	Días	Bugs/Día
1.1.1	1		1	329	0
1.1.2	28	3	31	273	0.11
1.1.3	14	2	16	237	0.07
1.1.4	15	2	17	182	0.09
1.1.5	215	18	233	59	3.98
1.1.6	37	8	45	195	0.23
Total Resultado	310	33	343	1274	0.27
Evolución de bugs de TOL resueltos al día por cada versión

## Informe 1
Filtro
product	- todo -
severidad	- todo -

Cantidad - bug_id		estado
Versión de último cambio	Versión de aparición	pendiente	postergado	resuelto	Total Resultado
1.1.1
	1.1.0			4	4
1.1.2
	1.1.0			3	3
	1.1.1	2	6	69	77
1.1.3
	1.1.1	3		4	7
	1.1.2	6	3	27	36
1.1.4
	1.1.0		1	1	2
	1.1.1		2	9	11
	1.1.2	1	2	20	23
	1.1.3	10	2	13	25
1.1.5
	1.1.0			12	12
	1.1.1		10	122	132
	1.1.2			47	47
	1.1.3	2	2	46	50
	1.1.4	4		12	16
1.1.6
	1.1.0			1	1
	1.1.1		1	4	5
	1.1.2			7	7
	1.1.3		1	10	11
	1.1.4	1		2	3
	1.1.5	11	3	33	47
Total Resultado		40	33	446	519

## Informe 2
Filtro
product	TOL
estado	resuelto

Cantidad - bug_id	severidad
Versión de último cambio	fallo	mejora	Total Resultado
1.1.1	1		1
1.1.2	28	3	31
1.1.3	14	2	16
1.1.4	15	2	17
1.1.5	215	18	233
1.1.6	37	8	45
Total Resultado	310	33	343

## Informe 3
Filtro
product	TOL
estado	- todo -

Cantidad - bug_id	severidad
Versión de aparición	fallo	mejora	Total Resultado
1.1.0	10	2	12
1.1.1	153	16	169
1.1.2	72	11	83
1.1.3	56	7	63
1.1.4	14		14
1.1.5	26	5	31
Total Resultado	331	41	372

## Informe 4
Filtro
product	TOL

Cantidad - bug_id	severidad
estado	fallo	mejora	Total Resultado
pendiente	9	1	10
postergado	12	7	19
resuelto	310	33	343
Total Resultado	331	41	372

## Informe 5
Filtro
product	- todo -

bug_severity		Distribución de la severidad de los bugs
blocker	83
critical	45
enhancement	75
major	72
minor	34
normal	195
trivial	15
Total Resultado	519

## Bugs
bug_id	opendate	changeddate	bug_severity	bug_status	resolution	product	short_short_desc	Versión de aparición	Versión de último cambio	severidad	estado
1	20/02/04 11:28	02/12/06 02:13	normal	RESOLVED	FIXED	TOL	frecuency function looses a unit after second period.	1.1.0	1.1.5	fallo	resuelto
2	26/02/04 20:12	02/12/06 02:13	trivial	RESOLVED	FIXED	TOL	BMTFile(Set): Additional carry return	1.1.0	1.1.5	fallo	resuelto
3	05/03/04 21:50	02/12/06 02:13	major	RESOLVED	FIXED	TOL	CholeskiInverse doesn't return the inverse matrix of the argument	1.1.0	1.1.5	fallo	resuelto
4	08/03/04 12:01	02/12/06 02:14	normal	RESOLVED	FIXED	TOL	Fallo en la funcion QuantileS()	1.1.0	1.1.5	fallo	resuelto
5	16/03/04 12:20	04/12/06 15:57	major	RESOLVED	FIXED	TOL	GSL libraries not correctly detected	1.1.0	1.1.5	fallo	resuelto
6	17/03/04 10:49	21/04/06 11:16	enhancement	RESOLVED	LATER	Tol-Base	Markers in graphs	1.1.0	1.1.4	mejora	postergado
7	17/03/04 12:12	17/03/04 18:13	normal	RESOLVED	FIXED	Tol-Base	Table gets destroyed when created from graph.	1.1.0	1.1.1	fallo	resuelto
8	17/03/04 17:06	29/04/04 12:23	minor	RESOLVED	FIXED	Tol-Base	Line color and fillups in graph options	1.1.0	1.1.2	fallo	resuelto
9	17/03/04 18:05	30/11/06 18:49	enhancement	RESOLVED	FIXED	Tol-Base	X Axis in Set's charts	1.1.0	1.1.5	mejora	resuelto
10	18/03/04 13:56	04/12/06 13:15	major	RESOLVED	FIXED	TOL	TimeSet global & TimeSet no global	1.1.0	1.1.5	fallo	resuelto
11	24/03/04 15:10	26/03/04 18:12	normal	RESOLVED	INVALID	TOL	diferent trace in function "Estimate"	1.1.0	1.1.1	fallo	resuelto
12	24/03/04 15:18	04/12/06 14:55	normal	RESOLVED	FIXED	TOL	The Estimate function gives back a wrong standard deviation	1.1.0	1.1.5	fallo	resuelto
13	24/03/04 19:27	24/03/04 19:28	major	RESOLVED	FIXED	Web	Bad default priority	1.1.0	1.1.1	fallo	resuelto
14	25/03/04 18:07	25/03/04 18:31	normal	RESOLVED	FIXED	Web	The TOL Component list for bugs reporting	1.1.0	1.1.1	fallo	resuelto
15	25/03/04 18:12	04/12/06 15:58	normal	RESOLVED	FIXED	TOL	Timing traces are not working	1.1.0	1.1.5	fallo	resuelto
16	30/03/04 13:17	19/04/06 17:11	trivial	RESOLVED	FIXED	Tol-Base	Bad work of Ctrl button	1.1.0	1.1.4	fallo	resuelto
17	30/03/04 14:07	06/11/07 10:41	enhancement	RESOLVED	FIXED	Web	Binary version	1.1.0	1.1.6	mejora	resuelto
18	01/04/04 11:47	04/12/06 15:09	blocker	RESOLVED	FIXED	TOL	Caída en compilación por la función IF	1.1.0	1.1.5	fallo	resuelto
19	01/04/04 15:36	04/12/06 16:23	enhancement	RESOLVED	FIXED	TOL	Round function and decimal number	1.1.0	1.1.5	mejora	resuelto
20	02/04/04 12:40	04/12/06 16:05	enhancement	RESOLVED	FIXED	TOL	logical, relational and arithmetic functions behaviour.	1.1.0	1.1.5	mejora	resuelto
21	02/04/04 13:20	27/08/04 16:20	minor	RESOLVED	FIXED	Tol-Base	Text code highlighting in TolBase Editor	1.1.0	1.1.2	fallo	resuelto
22	02/04/04 19:24	21/05/04 10:28	normal	RESOLVED	FIXED	Tol-Base	Syntax checking, Bayes SQL and connect fails	1.1.0	1.1.2	fallo	resuelto
23	06/04/04 12:04	04/12/06 16:09	major	RESOLVED	FIXED	TOL	Error in funcctions Include	1.1.1	1.1.5	fallo	resuelto
24	06/04/04 19:07	04/12/06 16:10	blocker	RESOLVED	FIXED	TOL	RationExpand to RatioExpand	1.1.1	1.1.5	fallo	resuelto
25	07/04/04 13:30	04/12/06 16:10	blocker	RESOLVED	FIXED	TOL	Real MinOutlierLikelyhood	1.1.1	1.1.5	fallo	resuelto
26	14/04/04 10:39	14/04/04 11:47	normal	RESOLVED	WONTFIX	Web	Components for TOL product bugs reporting about maths related problems	1.1.1	1.1.2	fallo	resuelto
27	22/04/04 18:15	22/04/04 18:29	normal	RESOLVED	WONTFIX	TOL	¿Series internas de Estimate globales?	1.1.1	1.1.2	fallo	resuelto
28	23/04/04 12:39	23/04/04 12:58	trivial	RESOLVED	FIXED	Tol-Base	Group and BinGroup Values are wrong	1.1.1	1.1.2	fallo	resuelto
29	23/04/04 15:34	04/12/06 16:27	normal	RESOLVED	FIXED	TOL	TolBase become blocked	1.1.1	1.1.5	fallo	resuelto
30	23/04/04 19:06	25/04/06 12:12	enhancement	RESOLVED	LATER	Tol-Base	Draw more than one timeset with a calendar	1.1.1	1.1.4	mejora	postergado
31	26/04/04 17:11	29/04/04 16:31	normal	RESOLVED	FIXED	Tol-Base	Inspecting an unamed TimeSet expression	1.1.1	1.1.2	fallo	resuelto
32	30/04/04 16:24	02/12/06 02:15	normal	RESOLVED	FIXED	TOL	Failure in Tol. It blocks when timeset is created.	1.1.1	1.1.5	fallo	resuelto
33	07/05/04 16:51	10/05/04 11:18	normal	RESOLVED	INVALID	TOL	About what 'DBOpen' and 'DBClose' functions should return	1.1.1	1.1.2	fallo	resuelto
34	07/05/04 16:58	19/10/05 10:15	normal	RESOLVED	FIXED	Tol-Base	copy' and 'paste' don´t work	1.1.1	1.1.3	fallo	resuelto
35	07/05/04 17:22	07/12/06 16:48	major	RESOLVED	LATER	TOL	PARSER ERROR	1.1.1	1.1.5	fallo	postergado
36	10/05/04 10:03	27/08/04 16:20	trivial	RESOLVED	LATER	Tol-Base	quotes have priority with respect to double slashes	1.1.1	1.1.2	fallo	postergado
37	10/05/04 10:43	04/12/06 17:22	trivial	RESOLVED	FIXED	TOL	variable name superior to the 267 characters	1.1.1	1.1.5	fallo	resuelto
38	10/05/04 13:29	07/12/06 16:49	enhancement	RESOLVED	FIXED	TOL	A new DBTable function	1.1.1	1.1.5	mejora	resuelto
39	12/05/04 12:12	04/12/06 17:24	normal	RESOLVED	FIXED	TOL	Parser returns a mistake always at the first line	1.1.1	1.1.5	fallo	resuelto
40	12/05/04 12:40	27/05/04 21:54	normal	RESOLVED	INVALID	TOL	Parser mistakes when the code contains a Struct that hasn´t been defined previously	1.1.1	1.1.2	fallo	resuelto
41	13/05/04 13:20	04/12/06 17:24	enhancement	RESOLVED	FIXED	TOL	we need a function returning the activity of a process	1.1.1	1.1.5	mejora	resuelto
42	18/05/04 19:11	04/12/06 17:35	normal	RESOLVED	FIXED	TOL	To compile a file without code	1.1.1	1.1.5	fallo	resuelto
43	19/05/04 14:48	19/05/04 16:35	enhancement	RESOLVED	INVALID	TOL	Kronecker Matrix Product	1.1.1	1.1.2	mejora	resuelto
44	19/05/04 16:38	04/12/06 17:40	major	RESOLVED	FIXED	TOL	SubCol does not return the correct columns.	1.1.1	1.1.5	fallo	resuelto
45	20/05/04 09:56	17/06/04 11:44	normal	RESOLVED	INVALID	TOL	Function Estimate sometimes doesn't work	1.1.1	1.1.2	fallo	resuelto
46	20/05/04 16:40	03/06/04 13:34	critical	RESOLVED	FIXED	TOL	To crash the TolBase when the file is decompile	1.1.1	1.1.2	fallo	resuelto
47	21/05/04 10:05	07/12/06 16:50	enhancement	RESOLVED	LATER	TOL	mechanisms of compilation halting	1.1.1	1.1.5	mejora	postergado
48	21/05/04 10:13	28/05/04 10:15	enhancement	RESOLVED	REMIND	Tol-Base	could be possible to make a copy of the object inspector?	1.1.1	1.1.2	mejora	postergado
49	24/05/04 13:57	02/12/06 01:40	enhancement	RESOLVED	LATER	TOL	LIKE function	1.1.1	1.1.5	mejora	postergado
50	25/05/04 11:15	04/12/06 17:41	normal	RESOLVED	FIXED	TOL	PutTableDateFormat' 'PutTableRealFormat'	1.1.1	1.1.5	fallo	resuelto
51	25/05/04 14:14	04/12/06 17:47	critical	RESOLVED	FIXED	TOL	tol crash	1.1.1	1.1.5	fallo	resuelto
52	27/05/04 17:19	04/12/06 17:57	normal	RESOLVED	FIXED	TOL	Density Functions Correction	1.1.1	1.1.5	fallo	resuelto
53	28/05/04 09:35	28/05/04 17:49	normal	RESOLVED	FIXED	Web	The bug's URL does not appear on the mails	1.1.1	1.1.2	fallo	resuelto
54	28/05/04 12:26	11/06/04 12:39	major	RESOLVED	DUPLICATE	Tol-Base	Project editor doesn't let include files with relative paths	1.1.1	1.1.2	fallo	resuelto
55	28/05/04 12:27	04/12/06 18:01	normal	RESOLVED	FIXED	TOL	Sobrecarga de operadores	1.1.1	1.1.5	fallo	resuelto
56	28/05/04 13:36	07/12/06 16:50	enhancement	RESOLVED	LATER	TOL	Enhancement of 'Show'	1.1.1	1.1.5	mejora	postergado
57	28/05/04 22:48	04/12/06 18:06	minor	RESOLVED	FIXED	TOL	Check syntax errors blocks TOLBase	1.1.1	1.1.5	fallo	resuelto
58	31/05/04 16:25	04/12/06 18:17	normal	RESOLVED	FIXED	TOL	BSIFile doesn´t create the associated BSDFile	1.1.1	1.1.5	fallo	resuelto
59	01/06/04 17:03	07/06/04 12:35	critical	RESOLVED	FIXED	Tol-Base	Series mapped to Y2 axis	1.1.1	1.1.2	fallo	resuelto
60	01/06/04 17:17	04/12/06 18:20	blocker	RESOLVED	FIXED	TOL	TOL get blocked when compling a file or just doing the syntax check	1.1.1	1.1.5	fallo	resuelto
61	01/06/04 17:39	04/12/06 18:21	blocker	RESOLVED	FIXED	Tol-Base	Using a TimeSet created from DatesOfSet for X Marker	1.1.1	1.1.5	fallo	resuelto
62	02/06/04 18:19	07/12/06 16:51	enhancement	RESOLVED	LATER	TOL	Problema de la funciï¿½ GibbsSampler	1.1.1	1.1.5	mejora	postergado
63	03/06/04 10:33	27/08/04 16:20	enhancement	RESOLVED	LATER	Tol-Base	Still problems on highlighting	1.1.1	1.1.2	mejora	postergado
64	03/06/04 10:47	04/12/06 18:27	critical	RESOLVED	FIXED	TOL	ill behaviour in assign operator	1.1.1	1.1.5	fallo	resuelto
65	08/06/04 15:52	04/12/06 18:29	critical	RESOLVED	FIXED	TOL	TOL does not give ERROR...	1.1.1	1.1.5	fallo	resuelto
66	08/06/04 18:03	04/12/06 18:33	blocker	RESOLVED	FIXED	TOL	use of -> operator in select function	1.1.1	1.1.5	fallo	resuelto
67	09/06/04 13:51	04/12/06 18:39	critical	RESOLVED	FIXED	TOL	tolbase crashes during evaluation	1.1.1	1.1.5	fallo	resuelto
68	09/06/04 16:10	04/12/06 18:41	critical	RESOLVED	FIXED	TOL	segmentation fault in Select evaluation	1.1.1	1.1.5	fallo	resuelto
69	09/06/04 18:29	04/12/06 18:41	trivial	RESOLVED	FIXED	TOL	an orthographic mistake in the description of 'ToName'	1.1.1	1.1.5	fallo	resuelto
70	09/06/04 19:53	17/06/04 14:13	enhancement	RESOLVED	FIXED	Tol-Base	several enhancements for projects	1.1.1	1.1.2	mejora	resuelto
71	10/06/04 20:56	04/12/06 18:44	major	RESOLVED	FIXED	TOL	TimeSet	1.1.1	1.1.5	fallo	resuelto
72	16/06/04 14:05	04/12/06 18:48	normal	RESOLVED	FIXED	TOL	Anything is not Anything	1.1.1	1.1.5	fallo	resuelto
73	19/06/04 00:35	22/06/04 18:05	blocker	RESOLVED	DUPLICATE	Tol-Base	Expresions not assigned to a explicit variable	1.1.1	1.1.2	fallo	resuelto
74	22/06/04 13:34	04/12/06 18:52	enhancement	RESOLVED	FIXED	TOL	Compiling problem whit anything variable	1.1.1	1.1.5	mejora	resuelto
75	22/06/04 13:52	27/02/06 10:38	normal	ASSIGNED		Tol-Base	Some wrong utilities of Ctrl	1.1.1	1.1.3	fallo	pendiente
76	24/06/04 16:35	24/06/04 17:00	normal	RESOLVED	INVALID	TOL	Sentences with queries altering the tables of a database return an error	1.1.1	1.1.2	fallo	resuelto
77	29/06/04 10:18	08/07/04 10:53	normal	RESOLVED	FIXED	Tol-Base	Bayes Sql don´t permit to use of numeric and text data	1.1.1	1.1.2	fallo	resuelto
78	30/06/04 10:29	04/12/06 18:52	major	RESOLVED	FIXED	TOL	Tol crash trying to view a void timeset	1.1.1	1.1.5	fallo	resuelto
79	02/07/04 09:44	04/12/06 19:16	normal	RESOLVED	FIXED	TOL	an error in SubSer and DatCh	1.1.1	1.1.5	fallo	resuelto
80	02/07/04 15:29	06/07/04 18:59	blocker	RESOLVED	FIXED	TOL	Crash TOL when used functions of construción of series by SQL	1.1.1	1.1.2	fallo	resuelto
81	06/07/04 09:57	04/12/06 19:18	normal	RESOLVED	FIXED	TOL	Dates of Estimate	1.1.1	1.1.5	fallo	resuelto
82	06/07/04 11:09	06/07/04 11:31	major	RESOLVED	INVALID	TOL	bug in SVD with negative eigenvalue matrices	1.1.1	1.1.2	fallo	resuelto
83	12/07/04 15:41	12/07/04 16:24	critical	RESOLVED	FIXED	Tol-Base	::tol::forallchild	1.1.1	1.1.2	fallo	resuelto
84	12/07/04 20:45	04/12/06 19:23	blocker	RESOLVED	FIXED	TOL	DatCh doesn't work	1.1.1	1.1.5	fallo	resuelto
85	14/07/04 09:44	02/12/06 02:15	normal	RESOLVED	FIXED	TOL	F-Snedecor Distribution	1.1.1	1.1.5	fallo	resuelto
86	14/07/04 11:03	14/07/04 12:40	normal	RESOLVED	FIXED	Web	When entering a new bug, page seems bad formated	1.1.1	1.1.2	fallo	resuelto
87	15/07/04 13:17	04/12/06 19:26	critical	RESOLVED	FIXED	TOL	Parser problem	1.1.1	1.1.5	fallo	resuelto
88	15/07/04 19:19	04/12/06 19:28	minor	RESOLVED	FIXED	TOL	And with one argument	1.1.1	1.1.5	fallo	resuelto
89	16/07/04 10:52	16/07/04 12:44	enhancement	RESOLVED	WONTFIX	Web	Posible mejora (durante el curso)	1.1.1	1.1.2	mejora	resuelto
90	16/07/04 10:58	19/07/04 09:44	enhancement	RESOLVED	WORKSFORME	Web	suggestion logo in english - change verb throw up	1.1.1	1.1.2	mejora	resuelto
91	16/07/04 16:03	09/05/06 12:51	normal	RESOLVED	WONTFIX	TOL	hidden virtual function	1.1.1	1.1.4	fallo	resuelto
92	19/07/04 11:58	04/12/06 19:28	normal	RESOLVED	FIXED	TOL	Global Variables Warning	1.1.1	1.1.5	fallo	resuelto
93	20/07/04 18:10	21/07/04 10:40	normal	RESOLVED	DUPLICATE	TOL	Tol crashes in a user defined function of Serie grammar	1.1.1	1.1.2	fallo	resuelto
94	20/07/04 19:29	20/07/04 19:39	normal	RESOLVED	DUPLICATE	TOL	Undestroyed global objects	1.1.1	1.1.2	fallo	resuelto
95	20/07/04 19:32	09/08/04 20:49	critical	RESOLVED	FIXED	TOL	Undestroyed global objects	1.1.1	1.1.2	fallo	resuelto
96	21/07/04 16:58	07/12/06 13:33	normal	RESOLVED	FIXED	TOL	Variables out of scope	1.1.1	1.1.5	fallo	resuelto
97	21/07/04 18:42	06/11/07 10:45	normal	RESOLVED	FIXED	TOL	Time sets C, Daily and Diario don't work with higher frequencies	1.1.1	1.1.6	fallo	resuelto
98	23/07/04 10:34	06/11/07 10:36	enhancement	RESOLVED	FIXED	Tol-Base	Add a shortcut to clear log in log window of tolbase	1.1.1	1.1.6	mejora	resuelto
99	26/07/04 23:07	05/10/04 10:20	normal	RESOLVED	INVALID	TOL	Functions with variable number of arguments: WinRmtSystem	1.1.1	1.1.2	fallo	resuelto
100	28/07/04 09:28	04/12/06 19:36	normal	RESOLVED	FIXED	TOL	Not recognize grammar inside structures	1.1.1	1.1.5	fallo	resuelto
101	28/07/04 18:39	04/12/06 19:40	enhancement	RESOLVED	FIXED	TOL	When multiplying wrong-sized matrix TOL does not give a warning.	1.1.1	1.1.5	mejora	resuelto
102	29/07/04 18:10	04/12/06 19:46	normal	RESOLVED	FIXED	TOL	Matrix definition	1.1.1	1.1.5	fallo	resuelto
103	04/08/04 13:37	04/12/06 19:47	minor	RESOLVED	FIXED	TOL	Missing ending quotes in the error message	1.1.1	1.1.5	fallo	resuelto
104	04/08/04 13:50	19/08/04 11:43	blocker	RESOLVED	FIXED	TOL	BDBOpen() and file not found -> TOL goes down	1.1.1	1.1.2	fallo	resuelto
105	04/08/04 14:21	18/08/04 15:45	major	ASSIGNED		TOL	BDBReg() loses one character in some lines	1.1.1	1.1.2	fallo	pendiente
106	04/08/04 14:24	08/08/04 11:10	blocker	RESOLVED	INVALID	TOL	BDBReg() crack (see bug 105)	1.1.1	1.1.2	fallo	resuelto
107	04/08/04 19:56	04/12/06 19:48	enhancement	RESOLVED	FIXED	TOL	No clear error: Type mismatch Real / Set	1.1.1	1.1.5	mejora	resuelto
108	04/08/04 20:20	08/08/04 11:07	blocker	RESOLVED	INVALID	TOL	GetDir() makes TOL crack inside a funtion	1.1.1	1.1.2	fallo	resuelto
109	04/08/04 20:56	04/12/06 19:52	blocker	RESOLVED	FIXED	TOL	A type in WriteLn() or Write() makes TOL Crack inside functions	1.1.1	1.1.5	fallo	resuelto
110	09/08/04 13:01	02/12/06 02:16	blocker	RESOLVED	FIXED	TOL	TimeSet Crack in succesor and intersection (Non progressive TimeSet?)	1.1.1	1.1.5	fallo	resuelto
111	09/08/04 13:30	27/02/06 10:40	minor	ASSIGNED		Tol-Base	A single quote in a remmark -> next remmark not in green	1.1.1	1.1.3	fallo	pendiente
112	09/08/04 13:58	02/12/06 02:16	minor	RESOLVED	FIXED	TOL	Sometimes A is not equal to ASCII(Char(A))	1.1.1	1.1.5	fallo	resuelto
113	09/08/04 14:39	29/09/04 01:32	minor	RESOLVED	LATER	Tol-Base	Bayes Editor: stranges movements with Alt + numeric keys	1.1.1	1.1.2	fallo	postergado
114	09/08/04 17:53	04/12/06 19:56	critical	RESOLVED	FIXED	TOL	Tol goes down with a erroneus (incomplete) series expresion	1.1.1	1.1.5	fallo	resuelto
115	10/08/04 17:53	04/12/06 19:59	normal	RESOLVED	FIXED	TOL	An error in '==' function	1.1.1	1.1.5	fallo	resuelto
116	11/08/04 13:46	30/08/04 13:00	normal	RESOLVED	FIXED	Tol-Base	no named objects can't be created	1.1.1	1.1.2	fallo	resuelto
117	11/08/04 14:08	18/08/04 16:06	normal	RESOLVED	FIXED	Web	I can't return from bug page to tol-project page	1.1.1	1.1.2	fallo	resuelto
118	13/08/04 11:32	18/08/04 16:18	blocker	RESOLVED	DUPLICATE	TOL	Tol crashes when making a "WriteLn" assigned to a "Text" type variable without name	1.1.1	1.1.2	fallo	resuelto
119	13/08/04 11:41	07/12/06 17:24	normal	RESOLVED	LATER	TOL	checkear sintaxis no captura ciertos errores	1.1.1	1.1.5	fallo	postergado
120	18/08/04 12:11	04/12/06 20:02	minor	RESOLVED	FIXED	TOL	A redifinition in an internal variable is shown as redefinition in a global variable	1.1.1	1.1.5	fallo	resuelto
121	18/08/04 17:56	16/09/04 13:27	minor	RESOLVED	FIXED	Tol-Base	TOLBase error when close the main window before a complete startup	1.1.1	1.1.2	fallo	resuelto
122	19/08/04 10:49	16/09/04 13:30	enhancement	RESOLVED	FIXED	Tol-Base	TOLEditor let open and edit the same file several times	1.1.1	1.1.2	mejora	resuelto
123	19/08/04 11:01	02/12/06 02:16	blocker	RESOLVED	FIXED	TOL	More than 2 empty lines at the end of BDT -> infinite loop	1.1.1	1.1.5	fallo	resuelto
124	19/08/04 11:10	30/08/04 11:37	enhancement	RESOLVED	FIXED	Tol-Base	Sometimes TOL and sometimes Tol	1.1.1	1.1.2	mejora	resuelto
125	19/08/04 11:22	07/09/04 11:31	minor	RESOLVED	FIXED	Tol-Base	TOLEditor not always open the Editor window	1.1.1	1.1.2	fallo	resuelto
126	19/08/04 11:27	25/04/06 12:34	enhancement	RESOLVED	INVALID	Tol-Base	TOLBase: resize internal windows -> a lot of shadow (wake?)	1.1.1	1.1.4	mejora	resuelto
127	19/08/04 11:43	27/08/04 13:09	minor	RESOLVED	FIXED	TOL	BDBOpen() and file not found -> a new empty file is created	1.1.1	1.1.2	fallo	resuelto
128	19/08/04 12:38	27/08/04 16:41	minor	RESOLVED	FIXED	Tol-Base	TolEditor: insert a € -> Select all text	1.1.1	1.1.2	fallo	resuelto
129	19/08/04 12:47	20/04/06 13:59	major	RESOLVED	FIXED	Tol-Base	TOLBase: Copy & close -> lose the clipboard	1.1.1	1.1.4	fallo	resuelto
130	19/08/04 13:32	04/12/06 20:08	major	RESOLVED	FIXED	TOL	DatCh() can lose the initial period	1.1.1	1.1.5	fallo	resuelto
131	19/08/04 13:51	10/09/04 11:18	minor	RESOLVED	FIXED	Tol-Base	TOLBase: The last open file is not a recent file	1.1.1	1.1.2	fallo	resuelto
132	19/08/04 16:22	05/12/06 10:56	normal	RESOLVED	FIXED	TOL	The same serie can be defined twice without any error or warning message	1.1.1	1.1.5	fallo	resuelto
133	24/08/04 12:44	25/08/04 14:07	critical	RESOLVED	FIXED	Tol-Base	I Can´t to add any node into a new TOL project.	1.1.1	1.1.2	fallo	resuelto
134	25/08/04 15:47	30/08/04 07:49	minor	RESOLVED	INVALID	TOL	Chart([[series]], file path) only works in TOLBase, not in TOL	1.1.1	1.1.2	fallo	resuelto
135	25/08/04 15:53	07/12/06 17:25	trivial	RESOLVED	LATER	TOL	Chart() Description don't say that the file is in gif format	1.1.1	1.1.5	fallo	postergado
136	25/08/04 16:39	13/09/04 10:28	minor	RESOLVED	FIXED	Tol-Base	Chart() permanent black border	1.1.1	1.1.2	fallo	resuelto
137	26/08/04 17:36	05/12/06 11:01	normal	RESOLVED	FIXED	TOL	Bad ReadFile behaviour	1.1.1	1.1.5	fallo	resuelto
138	27/08/04 13:12	27/08/04 13:12	major	ASSIGNED		Web	Dependency graph does not work	1.1.1	1.1.2	fallo	pendiente
139	01/09/04 12:48	05/12/06 11:03	normal	RESOLVED	FIXED	TOL	Function Description when you don´t define PutDescription	1.1.1	1.1.5	fallo	resuelto
140	01/09/04 17:31	10/10/06 19:55	normal	RESOLVED	INVALID	TOL	error of the 'Eval'	1.1.1	1.1.4	fallo	resuelto
141	01/09/04 18:35	01/09/04 19:50	major	RESOLVED	DUPLICATE	TOL	Eval dosen´t work	1.1.1	1.1.2	fallo	resuelto
142	03/09/04 18:28	05/12/06 11:03	normal	RESOLVED	FIXED	TOL	IsUnknown only takes reals	1.1.1	1.1.5	fallo	resuelto
143	07/09/04 10:35	05/12/06 11:10	blocker	RESOLVED	FIXED	TOL	Range Doesn`t work properly	1.1.1	1.1.5	fallo	resuelto
144	08/09/04 11:34	08/09/04 13:54	blocker	RESOLVED	FIXED	TOL	Tol version compatibility	1.1.1	1.1.2	fallo	resuelto
145	13/09/04 14:56	05/12/06 11:15	blocker	RESOLVED	FIXED	TOL	Inposible to re-assing local variables.	1.1.1	1.1.5	fallo	resuelto
146	13/09/04 16:51	05/12/06 11:20	normal	RESOLVED	FIXED	TOL	General scope error	1.1.1	1.1.5	fallo	resuelto
147	13/09/04 19:51	05/12/06 11:23	normal	RESOLVED	FIXED	TOL	an error in "In" function when initial and final date are equal	1.1.1	1.1.5	fallo	resuelto
148	14/09/04 13:26	05/12/06 11:30	normal	RESOLVED	FIXED	TOL	For returned type wrong parsed?	1.1.1	1.1.5	fallo	resuelto
149	15/09/04 13:12	01/10/04 10:39	normal	RESOLVED	FIXED	Tol-Base	double click/open file	1.1.1	1.1.2	fallo	resuelto
150	15/09/04 22:44	05/12/06 11:42	major	RESOLVED	FIXED	TOL	Problem with AutoCor functions	1.1.1	1.1.5	fallo	resuelto
151	16/09/04 13:18	16/09/04 17:45	enhancement	RESOLVED	FIXED	Tol-Base	Open tol file given as argument	1.1.1	1.1.2	mejora	resuelto
152	16/09/04 19:18	07/12/06 17:26	major	RESOLVED	FIXED	TOL	TOL Estimation seg faults when there is less data than variables.	1.1.1	1.1.5	fallo	resuelto
153	17/09/04 13:32	05/12/06 11:46	blocker	RESOLVED	FIXED	TOL	DistNormalInv DOES NOT WORK IN VERSION TolBase-CVS-20040913	1.1.1	1.1.5	fallo	resuelto
154	17/09/04 20:35	05/12/06 11:51	critical	RESOLVED	FIXED	TOL	DatCh doesnt work correctly again	1.1.1	1.1.5	fallo	resuelto
155	24/09/04 17:35	05/12/06 11:53	normal	RESOLVED	FIXED	TOL	Problem when accessing set elements by name	1.1.1	1.1.5	fallo	resuelto
156	24/09/04 17:42	27/02/06 10:49	normal	RESOLVED	FIXED	Tol-Base	Errors when resizing table columns by double-clicking on it's border.	1.1.1	1.1.3	fallo	resuelto
157	24/09/04 19:01	27/02/06 10:54	enhancement	RESOLVED	INVALID	Tol-Base	Wish: Resizing table windows	1.1.1	1.1.3	mejora	resuelto
158	24/09/04 19:05	27/02/06 10:46	enhancement	RESOLVED	FIXED	Tol-Base	Wish: Table column names	1.1.1	1.1.3	mejora	resuelto
159	27/09/04 10:30	01/10/04 10:38	normal	RESOLVED	WORKSFORME	Tol-Base	Calendar expert does not work	1.1.1	1.1.2	fallo	resuelto
160	27/09/04 11:58	13/10/04 11:29	minor	RESOLVED	FIXED	TOL	Wrong order when decompile the TIME SET	1.1.1	1.1.2	fallo	resuelto
161	27/09/04 17:40	05/12/06 11:54	normal	RESOLVED	FIXED	TOL	Estimating series with different datings produces an error but no warnings	1.1.1	1.1.5	fallo	resuelto
162	28/09/04 11:58	05/12/06 12:04	normal	RESOLVED	FIXED	TOL	TOL break down Polyn p2 = B^(2)* Real x;	1.1.1	1.1.5	fallo	resuelto
163	28/09/04 22:04	29/09/04 11:47	normal	RESOLVED	FIXED	TOL	Error in values "null" in the functions of access to Base of data	1.1.1	1.1.2	fallo	resuelto
164	01/10/04 16:26	05/12/06 12:11	major	RESOLVED	FIXED	TOL	TOL break down Serie out = (Real 0.8)* ser ;	1.1.1	1.1.5	fallo	resuelto
165	04/10/04 18:15	05/12/06 12:32	major	RESOLVED	FIXED	TOL	a random error in AIA function	1.1.1	1.1.5	fallo	resuelto
166	04/10/04 18:41	05/12/06 12:33	normal	RESOLVED	FIXED	TOL	I can't modify default dates of Tol	1.1.1	1.1.5	fallo	resuelto
167	04/10/04 20:56	02/12/06 02:17	normal	RESOLVED	FIXED	TOL	Efficiency problem when dealing with some TimeSet operations ?	1.1.1	1.1.5	fallo	resuelto
168	05/10/04 13:04	05/10/04 13:27	normal	RESOLVED	FIXED	Tol-Base	right click doesn`t work on Ratio objects	1.1.1	1.1.2	fallo	resuelto
169	06/10/04 10:31	05/12/06 11:52	normal	RESOLVED	DUPLICATE	TOL	Set result in estimate does not take odd names	1.1.1	1.1.5	fallo	resuelto
170	06/10/04 15:26	06/11/07 10:46	normal	RESOLVED	FIXED	TOL	Problems with DifEq and Estimate when using Gaussian	1.1.1	1.1.6	fallo	resuelto
171	06/10/04 17:57	05/12/06 12:34	normal	RESOLVED	FIXED	TOL	IncludeBMT is not able to load files with more than 4693 rows.	1.1.1	1.1.5	fallo	resuelto
172	06/10/04 23:15	05/12/06 12:34	normal	RESOLVED	FIXED	TOL	La versión 1.1.1 no compila bajándola de linux	1.1.1	1.1.5	fallo	resuelto
173	07/10/04 10:00	05/12/06 13:06	normal	RESOLVED	FIXED	TOL	Serie serExp = Exp(1)*CalInd( C, Diario) does not work	1.1.1	1.1.5	fallo	resuelto
174	07/10/04 14:34	05/12/06 12:39	normal	RESOLVED	FIXED	TOL	Serie ser_error = (a*b)*ser1 Does Not Work!	1.1.1	1.1.5	fallo	resuelto
175	07/10/04 16:57	27/02/06 11:12	enhancement	ASSIGNED		Tol-Base	some utilities for tables	1.1.1	1.1.3	mejora	pendiente
176	07/10/04 17:21	30/11/04 09:54	normal	RESOLVED	FIXED	Tol-Base	Tol Base se cae cuando se intenta dibujar intersección vacía	1.1.1	1.1.2	fallo	resuelto
177	08/10/04 10:58	05/12/06 12:40	normal	RESOLVED	FIXED	TOL	Serie ser1 = (-a)*ser2 does not create the serie	1.1.1	1.1.5	fallo	resuelto
178	08/10/04 16:45	09/10/04 14:03	normal	RESOLVED	DUPLICATE	TOL	Real out2 =!fun(0)+!fun(1)+!fun(0); Error!!	1.1.1	1.1.2	fallo	resuelto
179	08/10/04 16:45	05/12/06 12:52	normal	RESOLVED	FIXED	TOL	Real out2 =!fun(0)+!fun(1)+!fun(0); Error!!	1.1.1	1.1.5	fallo	resuelto
180	13/10/04 16:06	05/12/06 12:57	blocker	RESOLVED	FIXED	TOL	function doesn't exist	1.1.1	1.1.5	fallo	resuelto
181	13/10/04 19:50	13/10/04 20:28	blocker	RESOLVED	DUPLICATE	TOL	Evaluation in different level	1.1.1	1.1.2	fallo	resuelto
182	18/10/04 16:52	05/12/06 12:58	blocker	RESOLVED	FIXED	TOL	toltcl.dll doesn't compile in MSDev	1.1.1	1.1.5	fallo	resuelto
183	20/10/04 19:09	19/04/06 13:58	normal	RESOLVED	FIXED	Tol-Base	TolBase doesn't ask for saving files before being closed	1.1.1	1.1.4	fallo	resuelto
184	20/10/04 19:41	05/12/06 13:01	minor	RESOLVED	FIXED	TOL	A "white" character is included in FormatPolyn function	1.1.1	1.1.5	fallo	resuelto
185	20/10/04 23:20	05/12/06 13:01	blocker	RESOLVED	FIXED	TOL	Compiling error	1.1.1	1.1.5	fallo	resuelto
186	22/10/04 13:22	05/12/06 13:04	normal	RESOLVED	FIXED	TOL	Infinite loop when creating a Set with "Dates"	1.1.1	1.1.5	fallo	resuelto
187	25/10/04 10:40	02/12/06 02:17	normal	RESOLVED	FIXED	TOL	Some errors with "Range" function	1.1.1	1.1.5	fallo	resuelto
188	25/10/04 11:28	11/05/06 19:10	minor	RESOLVED	FIXED	Tol-Base	Opening non-existing files from command line	1.1.1	1.1.4	fallo	resuelto
189	25/10/04 13:12	19/04/06 13:56	enhancement	RESOLVED	INVALID	Tol-Base	About file Name in TOL Interface Editor...	1.1.1	1.1.4	mejora	resuelto
190	28/10/04 10:07	02/12/06 01:51	enhancement	RESOLVED	INVALID	TOL	In order to improve the error messages	1.1.1	1.1.5	mejora	resuelto
191	29/10/04 09:27	05/12/06 13:06	normal	RESOLVED	FIXED	TOL	Problems between BTsrFromReal and other Series	1.1.1	1.1.5	fallo	resuelto
192	02/11/04 17:29	04/11/04 17:29	normal	RESOLVED	FIXED	TOL	Using DbTable()	1.1.1	1.1.2	fallo	resuelto
193	10/11/04 14:09	10/01/05 18:28	critical	RESOLVED	INVALID	TOL	Local declaration treated as global into Set definitions	1.1.1	1.1.2	fallo	resuelto
194	12/11/04 00:59	05/12/06 13:08	normal	RESOLVED	FIXED	TOL	Fail in PutName function	1.1.1	1.1.5	fallo	resuelto
195	15/11/04 19:44	24/10/06 18:07	major	RESOLVED	REMIND	TOL	The mysterious dates	1.1.1	1.1.4	fallo	postergado
196	15/11/04 21:09	02/12/06 02:18	major	RESOLVED	FIXED	TOL	Y(), M() and M() do not work properly	1.1.1	1.1.5	fallo	resuelto
197	16/11/04 16:48	07/12/06 17:28	critical	RESOLVED	FIXED	TOL	Time causes a syntax error (TC alpha version)	1.1.1	1.1.5	fallo	resuelto
198	19/11/04 13:07	22/11/04 14:27	normal	RESOLVED	FIXED	Tol-Base	Matrix out = EQ(a, b); Does not work.	1.1.1	1.1.2	fallo	resuelto
199	20/11/04 00:05	05/12/06 13:09	blocker	RESOLVED	FIXED	TOL	ERROR in compile tol.dll project	1.1.1	1.1.5	fallo	resuelto
200	23/11/04 18:18	14/12/04 11:18	major	RESOLVED	REMIND	Tol-Base	Functions Matrix SetDiag , Matrix Diag	1.1.1	1.1.2	fallo	postergado
201	24/11/04 19:05	29/11/04 10:32	major	RESOLVED	DUPLICATE	TOL	what date should input start in Estimate function?	1.1.1	1.1.2	fallo	resuelto
202	25/11/04 16:17	05/12/06 13:12	major	RESOLVED	FIXED	TOL	error with timesets	1.1.1	1.1.5	fallo	resuelto
203	27/11/04 21:28	05/12/06 13:16	trivial	RESOLVED	FIXED	TOL	ERROR in ToName functions	1.1.1	1.1.5	fallo	resuelto
204	29/11/04 11:46	30/11/04 09:54	normal	RESOLVED	DUPLICATE	Tol-Base	Intersecciones vacías en TimeSet	1.1.1	1.1.2	fallo	resuelto
205	03/12/04 11:45	07/12/06 17:28	blocker	RESOLVED	FIXED	TOL	Error when we compile tol.dll	1.1.1	1.1.5	fallo	resuelto
206	03/12/04 14:45	02/12/06 02:18	major	RESOLVED	FIXED	TOL	estimates fail when the name of the input timeset isn´t the the name of the output timeset	1.1.1	1.1.5	fallo	resuelto
207	14/12/04 16:54	02/12/06 02:18	normal	RESOLVED	FIXED	TOL	The special character \ (back slash) yields an error	1.1.1	1.1.5	fallo	resuelto
208	16/12/04 12:15	20/04/06 13:48	enhancement	RESOLVED	FIXED	Tol-Base	Doesn`t exist the option "Save as" in the Project Editor	1.1.1	1.1.4	mejora	resuelto
209	16/12/04 18:33	21/12/04 11:02	normal	RESOLVED	FIXED	Tol-Base	drawing only points	1.1.1	1.1.2	fallo	resuelto
210	16/12/04 18:33	20/12/04 12:44	normal	RESOLVED	DUPLICATE	Tol-Base	drawing only points	1.1.1	1.1.2	fallo	resuelto
211	17/12/04 13:05	13/01/05 16:42	normal	RESOLVED	LATER	Tol-Base	Differences between "snapshot" or "filed" graphics	1.1.1	1.1.2	fallo	postergado
212	13/01/05 11:57	18/01/05 11:55	normal	RESOLVED	INVALID	TOL	Problema con series en minutal	1.1.1	1.1.2	fallo	resuelto
213	18/01/05 18:51	21/03/05 16:58	normal	RESOLVED	DUPLICATE	Tol-Base	::tol::info functions fails with function Recalc	1.1.1	1.1.2	fallo	resuelto
214	19/01/05 12:56	22/01/05 11:15	enhancement	RESOLVED	FIXED	TOL	MakeGlobal could improve its behavior	1.1.1	1.1.2	mejora	resuelto
215	20/01/05 16:56	05/12/06 13:20	blocker	RESOLVED	FIXED	TOL	Ceash with Arguments(), FindCode() and Struct	1.1.1	1.1.5	fallo	resuelto
216	21/01/05 10:05	05/12/06 13:28	minor	RESOLVED	FIXED	TOL	Function "Text Argumets". It does not use the optional parameters	1.1.1	1.1.5	fallo	resuelto
217	21/01/05 21:25	07/12/06 17:29	major	RESOLVED	REMIND	TOL	A variable's name can start with a number and only be a number	1.1.1	1.1.5	fallo	postergado
218	23/01/05 16:54	05/12/06 13:31	normal	RESOLVED	FIXED	TOL	Field operator is evaluated in left-side of an assignment expression	1.1.1	1.1.5	fallo	resuelto
219	24/01/05 19:22	05/12/06 13:32	normal	RESOLVED	FIXED	TOL	Creating more than one function with the same Name but with different Type	1.1.1	1.1.5	fallo	resuelto
220	25/01/05 12:55	07/12/06 17:29	enhancement	RESOLVED	REMIND	TOL	optional arguments in functions	1.1.1	1.1.5	mejora	postergado
221	26/01/05 11:55	05/12/06 13:33	normal	RESOLVED	FIXED	TOL	Problemas con SumS	1.1.1	1.1.5	fallo	resuelto
222	27/01/05 16:54	05/12/06 19:42	normal	RESOLVED	FIXED	TOL	About NIntegrate function...	1.1.1	1.1.5	fallo	resuelto
223	27/01/05 17:28	05/12/06 19:42	major	RESOLVED	FIXED	TOL	IntegrateQAG does not work!	1.1.1	1.1.5	fallo	resuelto
224	28/01/05 17:36	05/12/06 19:50	critical	RESOLVED	FIXED	TOL	error when estimating with a bad defined AR or MA set of Polyn	1.1.1	1.1.5	fallo	resuelto
225	01/02/05 15:43	05/12/06 19:53	major	RESOLVED	FIXED	TOL	Maybe a collateral damage in PutDescription with the new overload property	1.1.1	1.1.5	fallo	resuelto
226	01/02/05 16:18	05/12/06 19:57	major	RESOLVED	FIXED	TOL	Error in SetOfAnything with a declare Code objects	1.1.1	1.1.5	fallo	resuelto
227	01/02/05 19:00	05/12/06 20:00	critical	RESOLVED	FIXED	TOL	Reasignation operator := crashes when object doesn't exist	1.1.1	1.1.5	fallo	resuelto
228	03/02/05 13:13	03/02/05 13:41	normal	RESOLVED	FIXED	Tol-Base	This code does not work.	1.1.1	1.1.2	fallo	resuelto
229	03/02/05 13:36	05/12/06 20:20	normal	RESOLVED	FIXED	TOL	MonteCarloPlain does not work in Versión 1.1.2 Jan 13 2005 for WINDOWS	1.1.1	1.1.5	fallo	resuelto
230	04/02/05 09:47	05/12/06 20:23	major	RESOLVED	FIXED	TOL	ReplaceTable goes into and endless loop.	1.1.1	1.1.5	fallo	resuelto
231	07/02/05 11:36	11/02/05 10:42	normal	RESOLVED	INVALID	Tol-Base	For(1,0, Real(Real i) {i}) don´t give an error message	1.1.1	1.1.2	fallo	resuelto
232	08/02/05 12:05	02/12/06 02:19	normal	RESOLVED	FIXED	TOL	Polyn d = 1; Real bin = (Polyn 1 == Polyn d) ; Does not work ersión 1.1.2 Jan 13 2005 for WINDOWS	1.1.1	1.1.5	fallo	resuelto
233	08/02/05 13:47	05/12/06 20:30	normal	RESOLVED	FIXED	TOL	Set c = a-b don´t work with SetOfPolyn ( Ver. 1.1.2 Jan 13 2005 for WINDOWS)	1.1.1	1.1.5	fallo	resuelto
234	08/02/05 18:14	02/12/06 02:19	normal	RESOLVED	FIXED	TOL	Struct St ( Polyn a) fails evaluating polynomies (V 1.1.2 Jan 13 2005 for WINDOWS)	1.1.1	1.1.5	fallo	resuelto
235	09/02/05 09:12	07/11/07 12:53	normal	RESOLVED	LATER	TOL	Parsing problems with Matrix Literal declaration in a SetOfMatrix	1.1.1	1.1.6	fallo	postergado
236	09/02/05 11:07	02/12/06 02:19	normal	RESOLVED	FIXED	TOL	Range works bad	1.1.1	1.1.5	fallo	resuelto
237	09/02/05 11:52	05/12/06 20:33	blocker	RESOLVED	FIXED	TOL	Search for existing functions	1.1.1	1.1.5	fallo	resuelto
238	09/02/05 12:40	05/12/06 20:33	enhancement	RESOLVED	FIXED	TOL	FileRename	1.1.1	1.1.5	mejora	resuelto
239	09/02/05 12:58	02/12/06 02:19	normal	RESOLVED	FIXED	TOL	Embedded TimeSet functions causes TOL to die	1.1.1	1.1.5	fallo	resuelto
240	09/02/05 22:58	05/12/06 20:34	blocker	RESOLVED	FIXED	TOL	TOL crashes with common code lines	1.1.1	1.1.5	fallo	resuelto
241	11/02/05 14:36	11/02/05 20:07	blocker	RESOLVED	FIXED	Tol-Base	Click right botton in object inspector fails	1.1.1	1.1.2	fallo	resuelto
242	14/02/05 16:56	15/05/06 12:49	normal	RESOLVED	FIXED	Tol-Base	Capture information of a destroyed object	1.1.1	1.1.4	fallo	resuelto
243	24/02/05 00:49	21/03/05 11:48	major	RESOLVED	FIXED	Tol-Base	Exit from TolBase without saving edited files	1.1.1	1.1.2	fallo	resuelto
244	01/03/05 10:30	02/12/06 02:20	normal	RESOLVED	FIXED	TOL	Inclusion de matrices columnas	1.1.1	1.1.5	fallo	resuelto
245	10/03/05 19:52	06/11/07 10:50	critical	RESOLVED	FIXED	TOL	error in ObjectExist	1.1.1	1.1.6	fallo	resuelto
246	11/03/05 12:25	05/12/06 20:37	normal	RESOLVED	FIXED	TOL	TOL doesn't recognize local structs	1.1.1	1.1.5	fallo	resuelto
247	11/03/05 12:36	11/03/05 19:59	enhancement	RESOLVED	FIXED	TOL	MakeGlobal allows only left-evaluable expressions	1.1.1	1.1.2	mejora	resuelto
248	11/03/05 15:15	21/03/05 16:58	normal	RESOLVED	FIXED	Tol-Base	ERROR: Forbidden BText access 0 < -1 < 0	1.1.1	1.1.2	fallo	resuelto
249	17/03/05 13:39	05/12/06 20:38	blocker	RESOLVED	FIXED	TOL	SubSer returns nulls at the end of an estimated residuals	1.1.1	1.1.5	fallo	resuelto
250	22/03/05 11:45	07/12/06 17:31	major	RESOLVED	REMIND	TOL	The function "While" is aproximately 4 times slower than the function "For" or "Eval"	1.1.1	1.1.5	fallo	postergado
251	01/04/05 17:31	05/12/06 20:39	enhancement	RESOLVED	FIXED	TOL	Quantiles	1.1.1	1.1.5	mejora	resuelto
252	18/04/05 18:50	30/01/07 18:41	normal	RESOLVED	FIXED	Tol-Base	bug when "decompiling"	1.1.1	1.1.5	fallo	resuelto
253	19/04/05 11:31	02/12/06 02:20	normal	RESOLVED	FIXED	TOL	Error en Complex	1.1.1	1.1.5	fallo	resuelto
254	19/04/05 13:36	05/12/06 20:41	normal	RESOLVED	FIXED	TOL	Error en la sentencia interseccion de conjuntos	1.1.1	1.1.5	fallo	resuelto
255	26/04/05 12:54	22/12/05 11:39	enhancement	RESOLVED	FIXED	TOL	DBTableColumn Prefix	1.1.2	1.1.3	mejora	resuelto
256	09/05/05 16:16	23/06/05 13:19	enhancement	RESOLVED	FIXED	Tol-Base	New graphic options	1.1.2	1.1.3	mejora	resuelto
257	09/05/05 18:54	09/05/05 21:05	normal	RESOLVED	FIXED	TOL	DBCreateSeriesTable doesn't work	1.1.2	1.1.3	fallo	resuelto
258	10/05/05 11:03	18/04/06 16:24	normal	RESOLVED	DUPLICATE	Tol-Base	TimeSet tm = WD(6)*WD(7); Calendar Expert breaks down TOL.	1.1.2	1.1.4	fallo	resuelto
259	10/05/05 19:29	12/05/05 12:41	normal	RESOLVED	FIXED	TOL	First date of any year, in any Serie, is not stored in DDBB	1.1.2	1.1.3	fallo	resuelto
260	12/05/05 00:24	16/05/05 12:45	major	RESOLVED	INVALID	TOL	Same TimeSet in input and output makes Estimate to crash	1.1.2	1.1.3	fallo	resuelto
261	12/05/05 11:56	12/05/05 12:06	normal	RESOLVED	INVALID	TOL	Union of Sets doesn't work	1.1.2	1.1.3	fallo	resuelto
262	13/05/05 15:08	05/12/06 20:44	minor	RESOLVED	FIXED	TOL	Different out grammar makes TOL to crash with FindCode	1.1.2	1.1.5	fallo	resuelto
263	18/05/05 19:01	05/12/06 20:51	normal	RESOLVED	FIXED	TOL	No casting is performed over an element of a Set	1.1.2	1.1.5	fallo	resuelto
264	18/05/05 19:03	05/12/06 20:53	blocker	RESOLVED	FIXED	TOL	Error in the Estmate	1.1.2	1.1.5	fallo	resuelto
265	18/05/05 19:19	18/05/05 19:26	normal	RESOLVED	DUPLICATE	TOL	Set and SetOfPolyn	1.1.2	1.1.3	fallo	resuelto
266	20/05/05 18:10	06/11/07 10:37	enhancement	RESOLVED	FIXED	Tol-Base	Decopile in 'Archivos incluidos' window with F8	1.1.2	1.1.6	mejora	resuelto
267	23/05/05 10:54	07/12/06 10:58	critical	RESOLVED	FIXED	TOL	FormatDate()	1.1.2	1.1.5	fallo	resuelto
268	23/05/05 16:00	07/12/06 10:58	major	RESOLVED	FIXED	TOL	A random fatal error makes to crash compilation of tol.dll	1.1.2	1.1.5	fallo	resuelto
269	24/05/05 12:34	18/04/06 16:26	normal	RESOLVED	DUPLICATE	TOL	Error de interseccion en TimeSets	1.1.2	1.1.4	fallo	resuelto
270	26/05/05 01:10	07/12/06 11:04	normal	RESOLVED	FIXED	TOL	Include BST removes tailing spaces of text elements	1.1.2	1.1.5	fallo	resuelto
271	27/05/05 21:24	02/12/06 02:20	normal	RESOLVED	FIXED	TOL	Tol crushes witn a negative Succ() - In() TimeSet	1.1.2	1.1.5	fallo	resuelto
272	31/05/05 21:18	01/06/05 09:25	major	RESOLVED	FIXED	TOL	DBSeries returns no named series	1.1.2	1.1.3	fallo	resuelto
273	17/06/05 09:54	02/12/06 02:20	major	RESOLVED	FIXED	TOL	Date Succ(date, timeSet, -k), with k>0	1.1.2	1.1.5	fallo	resuelto
274	19/06/05 16:51	07/12/06 11:07	major	RESOLVED	FIXED	TOL	Try to access a no declare variable causes TOL to break down	1.1.2	1.1.5	fallo	resuelto
275	20/06/05 18:19	07/11/07 12:54	normal	RESOLVED	FIXED	TOL	ACF, PACF, IACF and IPACF in 64bits architecture	1.1.2	1.1.6	fallo	resuelto
276	29/06/05 12:42	07/11/07 12:59	normal	RESOLVED	FIXED	TOL	Decompilation ?	1.1.2	1.1.6	fallo	resuelto
277	29/06/05 13:20	07/11/07 15:46	enhancement	RESOLVED	FIXED	TOL	Tcl_Eval (Tcl support with LoadLib)	1.1.2	1.1.6	mejora	resuelto
278	30/06/05 12:06	22/07/05 17:03	normal	RESOLVED	LATER	Tol-Base	Indentation	1.1.2	1.1.3	fallo	postergado
279	30/06/05 12:08	21/04/06 11:05	normal	RESOLVED	LATER	Tol-Base	Contextual menu on the left side of the inspector	1.1.2	1.1.4	fallo	postergado
280	01/07/05 13:39	02/12/06 02:21	normal	RESOLVED	FIXED	TOL	reparacion en IncludeBDT	1.1.2	1.1.5	fallo	resuelto
281	05/07/05 09:34	07/07/05 18:44	enhancement	RESOLVED	FIXED	TOL	GlobalizeSeries enhancement	1.1.2	1.1.3	mejora	resuelto
282	13/07/05 10:42	27/02/06 10:45	normal	ASSIGNED		Tol-Base	Gui Functions...	1.1.2	1.1.3	fallo	pendiente
283	14/07/05 02:19	07/12/06 11:32	blocker	RESOLVED	FIXED	TOL	TolBase falls in error	1.1.2	1.1.5	fallo	resuelto
284	14/07/05 14:43	02/12/06 02:21	major	RESOLVED	FIXED	TOL	Acess to Set elements by name	1.1.2	1.1.5	fallo	resuelto
285	14/07/05 16:45	14/07/05 16:47	normal	RESOLVED	DUPLICATE	TOL	Access element of the Set by name	1.1.2	1.1.3	fallo	resuelto
286	18/07/05 11:20	02/12/06 02:21	normal	RESOLVED	FIXED	TOL	Set function Range returns wrong number of elements	1.1.2	1.1.5	fallo	resuelto
287	18/07/05 11:39	07/12/06 12:10	blocker	RESOLVED	FIXED	TOL	Include and IncludeMatrix dont work	1.1.2	1.1.5	fallo	resuelto
288	26/07/05 16:00	08/08/05 12:33	enhancement	RESOLVED	FIXED	Tol-Base	To detect when a file has been changed	1.1.2	1.1.3	mejora	resuelto
289	05/08/05 10:36	27/02/06 10:40	normal	ASSIGNED		Tol-Base	Editor Enhancement	1.1.2	1.1.3	fallo	pendiente
290	20/08/05 17:42	02/12/06 02:21	major	RESOLVED	FIXED	TOL	Error in SetOfText	1.1.2	1.1.5	fallo	resuelto
291	23/08/05 18:44	21/04/06 10:47	trivial	RESOLVED	FIXED	Tol-Base	BDT Inclusion from Network Path	1.1.2	1.1.4	fallo	resuelto
292	26/08/05 14:04	29/08/05 11:33	critical	RESOLVED	INVALID	TOL	Estimate produces huge residuals when RelativeTolerance=0.0001	1.1.2	1.1.3	fallo	resuelto
293	31/08/05 18:26	02/12/06 02:22	critical	RESOLVED	FIXED	TOL	Error en el fechado Mes 445	1.1.2	1.1.5	fallo	resuelto
294	06/09/05 10:37	16/02/07 13:49	normal	RESOLVED	FIXED	TOL	Types nonrecognized in MySql	1.1.2	1.1.5	fallo	resuelto
295	06/09/05 12:11	16/02/07 13:49	normal	RESOLVED	DUPLICATE	TOL	Types nonrecognized in MySql	1.1.2	1.1.5	fallo	resuelto
296	06/09/05 17:37	16/02/07 13:48	critical	RESOLVED	FIXED	TOL	non-recognized types of fields in a query to MySql	1.1.2	1.1.5	fallo	resuelto
297	06/09/05 17:52	02/12/06 01:15	normal	RESOLVED	DUPLICATE	TOL	Error en la función TextMatch	1.1.2	1.1.5	fallo	resuelto
298	06/09/05 17:55	02/12/06 02:22	normal	RESOLVED	FIXED	TOL	Error en la inserción de ficheros bst	1.1.2	1.1.5	fallo	resuelto
299	06/09/05 18:13	18/07/06 09:51	critical	RESOLVED	INVALID	TOL	Dont connecting by tol to mysql database	1.1.2	1.1.4	fallo	resuelto
300	07/09/05 01:50	21/11/06 10:39	normal	RESOLVED	FIXED	TOL	Unknow data type bigint in ODBC to MySQL	1.1.2	1.1.4	fallo	resuelto
301	07/09/05 12:12	02/12/06 02:22	major	RESOLVED	FIXED	TOL	Conjunto temporal no progresivo	1.1.2	1.1.5	fallo	resuelto
302	07/09/05 13:54	04/10/05 16:20	normal	RESOLVED	FIXED	Tol-Base	Crear una tabla copiando datos de Excel	1.1.2	1.1.3	fallo	resuelto
303	09/09/05 20:27	07/12/06 12:10	critical	RESOLVED	FIXED	TOL	Error when include a bmt file	1.1.2	1.1.5	fallo	resuelto
304	09/09/05 22:31	18/10/05 15:28	normal	RESOLVED	FIXED	Tol-Base	SADD TCL/TK projeto prjTelespTrafico	1.1.2	1.1.3	fallo	resuelto
305	13/09/05 20:32	02/12/06 02:23	major	RESOLVED	FIXED	TOL	SubSer error	1.1.2	1.1.5	fallo	resuelto
306	15/09/05 16:17	15/09/05 16:17	normal	NEW		TOL	Error in DBTableColumn?	1.1.2	1.1.3	fallo	pendiente
307	16/09/05 12:23	07/12/06 12:24	normal	RESOLVED	FIXED	TOL	Error in DatCh	1.1.2	1.1.5	fallo	resuelto
308	26/09/05 20:57	19/04/06 17:15	normal	RESOLVED	FIXED	Tol-Base	Problem with replace all	1.1.2	1.1.4	fallo	resuelto
309	27/09/05 15:30	27/09/05 16:33	trivial	RESOLVED	INVALID	TOL	PutStructure doesn't work	1.1.2	1.1.3	fallo	resuelto
310	28/09/05 17:45	24/10/06 13:49	major	RESOLVED	FIXED	TOL	Not Allowed Series names in DBSeries* functions	1.1.2	1.1.4	fallo	resuelto
311	28/09/05 23:06	27/10/05 10:54	normal	RESOLVED	FIXED	Tol-Base	Error decompiling file and including a file with blankspace	1.1.2	1.1.3	fallo	resuelto
312	30/09/05 12:35	02/12/06 02:23	enhancement	RESOLVED	FIXED	TOL	An improvement for TextToDate function	1.1.2	1.1.5	mejora	resuelto
313	30/09/05 17:30	02/05/06 13:40	enhancement	RESOLVED	DUPLICATE	TOL	BDTFile Function enchancement. Urgent	1.1.2	1.1.4	mejora	resuelto
314	03/10/05 16:02	18/10/05 16:21	enhancement	RESOLVED	LATER	Tol-Base	desactivate series of a graph	1.1.2	1.1.3	mejora	postergado
315	04/10/05 17:02	02/12/06 02:23	normal	RESOLVED	FIXED	TOL	Succ(Succ ..)	1.1.2	1.1.5	fallo	resuelto
316	05/10/05 13:31	27/10/05 10:54	normal	RESOLVED	DUPLICATE	Tol-Base	Removal of Inserted File	1.1.2	1.1.3	fallo	resuelto
317	10/10/05 11:23	02/12/06 02:23	blocker	RESOLVED	FIXED	TOL	critical Error in tol	1.1.2	1.1.5	fallo	resuelto
318	10/10/05 18:34	02/12/06 02:24	major	RESOLVED	FIXED	TOL	Error compiling	1.1.2	1.1.5	fallo	resuelto
319	14/10/05 09:53	04/05/06 16:52	enhancement	RESOLVED	FIXED	TOL	Struct function can yield a TOL failure	1.1.2	1.1.4	mejora	resuelto
320	17/10/05 12:34	23/10/05 17:37	normal	RESOLVED	FIXED	Tol-Base	Last row is not showed in a query with text	1.1.2	1.1.3	fallo	resuelto
321	17/10/05 13:03	18/10/05 15:17	normal	RESOLVED	INVALID	TOL	Grammar in DBTable	1.1.2	1.1.3	fallo	resuelto
322	17/10/05 13:06	02/05/06 12:50	normal	RESOLVED	INVALID	TOL	line jump	1.1.2	1.1.4	fallo	resuelto
323	18/10/05 15:10	02/05/06 11:35	minor	RESOLVED	WONTFIX	TOL	Operator precedence between [] and ->	1.1.2	1.1.4	fallo	resuelto
324	20/10/05 11:21	07/12/06 12:33	blocker	RESOLVED	FIXED	TOL	constantes	1.1.2	1.1.5	fallo	resuelto
325	24/10/05 11:30	28/10/05 12:17	minor	RESOLVED	FIXED	Tol-Base	a warning message appears when you make a table from a time series graphic	1.1.2	1.1.3	fallo	resuelto
326	24/10/05 11:52	07/12/06 12:37	enhancement	RESOLVED	FIXED	TOL	enhancement for BinGroup function	1.1.2	1.1.5	mejora	resuelto
327	24/10/05 14:56	25/10/05 09:46	normal	RESOLVED	INVALID	TOL	Bug in SetSer function	1.1.2	1.1.3	fallo	resuelto
328	25/10/05 11:25	07/12/06 12:39	blocker	RESOLVED	FIXED	TOL	no incluye las bsi	1.1.2	1.1.5	fallo	resuelto
329	25/10/05 21:17	10/11/05 10:36	normal	ASSIGNED		Tol-Base	Error in retrieving Oracle Integer data	1.1.2	1.1.3	fallo	pendiente
330	02/11/05 09:40	07/12/06 12:43	normal	RESOLVED	FIXED	TOL	Sort function	1.1.2	1.1.5	fallo	resuelto
331	03/11/05 10:53	07/12/06 12:44	enhancement	RESOLVED	FIXED	TOL	convert objects without an explicit type	1.1.2	1.1.5	mejora	resuelto
332	03/11/05 11:03	07/12/06 12:44	enhancement	RESOLVED	FIXED	TOL	solving some problem with BinGroup	1.1.2	1.1.5	mejora	resuelto
333	07/11/05 11:30	15/11/05 10:11	normal	RESOLVED	FIXED	Tol-Base	functions associated to Object Inspector elements	1.1.2	1.1.3	fallo	resuelto
334	10/11/05 13:16	19/04/06 17:02	minor	RESOLVED	DUPLICATE	Tol-Base	Problem with Replace All	1.1.2	1.1.4	fallo	resuelto
335	14/11/05 17:33	07/12/06 17:32	major	RESOLVED	FIXED	TOL	Include with F11 (Eval Window)	1.1.2	1.1.5	fallo	resuelto
336	18/11/05 13:17	23/05/06 10:47	blocker	RESOLVED	FIXED	TOL	ERROR: (Funcion DBSeriesTable)	1.1.2	1.1.4	fallo	resuelto
337	23/11/05 10:25	23/11/05 10:25	blocker	NEW		TOL	ODBC Types and Databases in Teradata	1.1.2	1.1.3	fallo	pendiente
338	24/11/05 14:08	07/12/06 12:49	normal	RESOLVED	FIXED	TOL	problem with the conjugation complex	1.1.2	1.1.5	fallo	resuelto
339	25/11/05 14:53	17/02/06 17:38	normal	RESOLVED	FIXED	Tol-Base	Problem matrix graphic	1.1.2	1.1.3	fallo	resuelto
340	09/12/05 09:34	02/12/06 02:24	enhancement	RESOLVED	FIXED	TOL	Statistic function in DatCh	1.1.2	1.1.5	mejora	resuelto
341	21/12/05 20:04	02/12/06 02:24	blocker	RESOLVED	FIXED	TOL	ERROR Estimate	1.1.2	1.1.5	fallo	resuelto
342	22/12/05 19:34	07/12/06 12:50	enhancement	RESOLVED	FIXED	TOL	"Show" function shows "Include" traces	1.1.2	1.1.5	mejora	resuelto
343	29/12/05 16:22	27/02/06 11:07	normal	ASSIGNED		Tol-Base	.prj files are not well formed to be readable by TOL	1.1.2	1.1.3	fallo	pendiente
344	20/01/06 16:12	07/11/07 15:49	blocker	RESOLVED	FIXED	TOL	Tol is unable to free memory	1.1.2	1.1.6	fallo	resuelto
345	24/01/06 11:43	19/04/06 17:16	minor	RESOLVED	FIXED	Tol-Base	F3 search again only searchs for the first word	1.1.2	1.1.4	fallo	resuelto
346	26/01/06 19:29	06/11/07 10:54	normal	RESOLVED	FIXED	TOL	1+1+1 Not Equal SetSun(SetOfReal(1,1,1))	1.1.2	1.1.6	fallo	resuelto
347	26/01/06 19:35	07/12/06 12:51	trivial	RESOLVED	FIXED	TOL	Syntax analyser , can not find this error	1.1.2	1.1.5	fallo	resuelto
348	07/02/06 13:25	19/04/06 17:19	normal	RESOLVED	FIXED	Tol-Base	Compiling New File without saving	1.1.2	1.1.4	fallo	resuelto
349	07/02/06 17:30	24/10/06 18:47	blocker	ASSIGNED		TOL	Problems selecting integral values from oracle database.	1.1.2	1.1.4	fallo	pendiente
350	07/02/06 21:13	02/12/06 02:25	normal	RESOLVED	FIXED	Tol-Base	Series definition with Include inside "{ }"	1.1.2	1.1.5	fallo	resuelto
351	08/02/06 11:12	02/12/06 02:25	major	RESOLVED	FIXED	TOL	Unknown crash in Serie function	1.1.2	1.1.5	fallo	resuelto
352	09/02/06 18:34	02/12/06 02:25	normal	RESOLVED	FIXED	TOL	Table Function	1.1.2	1.1.5	fallo	resuelto
353	09/02/06 20:08	19/04/06 17:20	enhancement	RESOLVED	FIXED	Tol-Base	Sintaxis check error window can`t be closed with 'Esc' key	1.1.2	1.1.4	mejora	resuelto
354	14/02/06 15:19	07/12/06 12:54	major	RESOLVED	FIXED	TOL	Bad working of DatCh or SerTms function	1.1.2	1.1.5	fallo	resuelto
355	16/02/06 13:53	16/02/06 16:33	major	RESOLVED	INVALID	TOL	A problem whith CalInd sintax	1.1.2	1.1.3	fallo	resuelto
356	16/02/06 16:11	21/04/06 11:03	normal	RESOLVED	FIXED	Tol-Base	Problems sending series to spool	1.1.2	1.1.4	fallo	resuelto
357	22/02/06 12:11	07/12/06 12:55	normal	RESOLVED	FIXED	TOL	An error in GetDir function	1.1.2	1.1.5	fallo	resuelto
358	22/02/06 17:08	22/02/06 17:59	major	RESOLVED	LATER	TOL	Strange behaviour when downloading series from database.	1.1.2	1.1.3	fallo	postergado
359	23/02/06 18:56	23/02/06 20:36	normal	RESOLVED	FIXED	TOL	Problem creating series at global scope.	1.1.2	1.1.3	fallo	resuelto
360	24/02/06 11:19	24/02/06 13:33	normal	RESOLVED	FIXED	Web	In the OS combo for bug reporting Windows XP is missing.	1.1.2	1.1.3	fallo	resuelto
361	01/03/06 12:51	20/03/06 12:12	normal	RESOLVED	FIXED	TOL	crash in compile- decompile - compile with Struct	1.1.2	1.1.4	fallo	resuelto
362	01/03/06 18:17	05/05/06 12:35	normal	RESOLVED	FIXED	Tol-Base	crash in tol::info reference	1.1.2	1.1.4	fallo	resuelto
363	03/03/06 21:59	07/11/07 16:12	normal	RESOLVED	FIXED	TOL	Problem with DBSeries	1.1.2	1.1.6	fallo	resuelto
364	09/03/06 12:27	16/03/06 12:44	blocker	RESOLVED	FIXED	TOL	SQL returned type is not readable	1.1.2	1.1.3	fallo	resuelto
365	10/03/06 15:01	28/03/06 09:48	minor	RESOLVED	LATER	Tol-Base	Bars Graphic in two Y axis	1.1.2	1.1.4	fallo	postergado
366	15/03/06 12:01	07/12/06 12:55	trivial	RESOLVED	FIXED	TOL	Description of the FirstToUpper function	1.1.2	1.1.5	fallo	resuelto
367	17/03/06 10:17	20/03/06 12:12	blocker	RESOLVED	DUPLICATE	TOL	a problem with Structs? TOLBase falls down	1.1.2	1.1.4	fallo	resuelto
368	21/03/06 20:12	02/12/06 02:25	normal	RESOLVED	FIXED	TOL	The parser can't recognize a non-sense code.	1.1.3	1.1.5	fallo	resuelto
369	24/03/06 12:15	25/04/06 12:15	normal	RESOLVED	FIXED	Tol-Base	Find window can't remember the option "fit captial and small letters"	1.1.3	1.1.4	fallo	resuelto
370	24/03/06 16:42	07/12/06 12:56	enhancement	RESOLVED	FIXED	TOL	Peticion para calculo de los residuos iniciales de un modelo ARIMA	1.1.3	1.1.5	mejora	resuelto
371	27/03/06 11:28	02/12/06 02:26	enhancement	RESOLVED	FIXED	TOL	export of data of a set-table	1.1.3	1.1.5	mejora	resuelto
372	27/03/06 18:40	09/05/06 15:48	normal	ASSIGNED		Tol-Base	Set column types	1.1.3	1.1.4	fallo	pendiente
373	28/03/06 15:56	20/04/06 12:13	enhancement	RESOLVED	LATER	Tol-Base	Object inspector can't remember the width of the columns	1.1.3	1.1.4	mejora	postergado
374	29/03/06 13:31	02/12/06 02:26	major	RESOLVED	FIXED	TOL	Unordered timeset problem.	1.1.3	1.1.5	fallo	resuelto
375	29/03/06 17:44	07/12/06 17:33	normal	CLOSED	REMIND	TOL	Compilation errors	1.1.3	1.1.5	fallo	postergado
376	30/03/06 21:00	07/12/06 17:34	normal	RESOLVED	FIXED	TOL	Problem when creating a long set of dates	1.1.3	1.1.5	fallo	resuelto
377	30/03/06 23:12	02/12/06 02:27	major	RESOLVED	FIXED	TOL	Problem in defining real numbers in scientific format	1.1.3	1.1.5	fallo	resuelto
378	31/03/06 17:13	02/12/06 02:27	normal	RESOLVED	FIXED	TOL	Error using Estimate	1.1.3	1.1.5	fallo	resuelto
379	03/04/06 16:53	02/12/06 02:27	critical	RESOLVED	FIXED	TOL	Problem when including a text	1.1.3	1.1.5	fallo	resuelto
380	03/04/06 16:54	03/04/06 17:05	critical	RESOLVED	DUPLICATE	TOL	Problem when including a text	1.1.3	1.1.4	fallo	resuelto
381	06/04/06 11:29	06/04/06 11:29	normal	NEW		TOL	DBTable function fails when accessing real fields of an Oracle92 table	1.1.3	1.1.4	fallo	pendiente
382	11/04/06 16:02	02/12/06 02:27	critical	RESOLVED	FIXED	TOL	problem accessing Succ(Succ (TS, negative integer, TS),negative integer,TS)	1.1.3	1.1.5	fallo	resuelto
383	11/04/06 19:54	02/12/06 02:27	blocker	RESOLVED	FIXED	TOL	Estimate makes TOL crash when ModelDef has a wrong bad definition	1.1.3	1.1.5	fallo	resuelto
384	12/04/06 22:45	29/04/06 21:50	minor	RESOLVED	FIXED	Tol-Base	Problem with TOL variable Language	1.1.3	1.1.4	fallo	resuelto
385	25/04/06 16:52	26/04/06 17:32	enhancement	RESOLVED	FIXED	Tol-Base	Compile till node enhancement	1.1.3	1.1.4	mejora	resuelto
386	25/04/06 17:17	26/04/06 17:41	normal	RESOLVED	FIXED	Tol-Base	Cannot compile	1.1.3	1.1.4	fallo	resuelto
387	25/04/06 19:23	07/12/06 12:59	normal	RESOLVED	FIXED	TOL	Segmentation fault in FormatReal	1.1.3	1.1.5	fallo	resuelto
388	25/04/06 19:36	02/12/06 02:28	critical	RESOLVED	FIXED	TOL	Problem with adding matrices	1.1.3	1.1.5	fallo	resuelto
389	25/04/06 19:51	07/11/07 21:01	minor	RESOLVED	FIXED	TOL	strange error message in DBCreateSeriesTable	1.1.3	1.1.6	fallo	resuelto
390	26/04/06 14:57	02/12/06 02:28	critical	RESOLVED	FIXED	TOL	Problem with DistNormalInv	1.1.3	1.1.5	fallo	resuelto
391	03/05/06 13:14	07/11/07 16:08	blocker	RESOLVED	FIXED	TOL	An access to a function result (with SQL Server connection) produces a TOL crash	1.1.3	1.1.6	fallo	resuelto
392	04/05/06 18:47	07/11/07 16:12	enhancement	RESOLVED	FIXED	TOL	Real Format in MetropolisHastings	1.1.3	1.1.6	mejora	resuelto
393	05/05/06 16:14	07/11/07 16:12	enhancement	RESOLVED	FIXED	TOL	Error Messages provenient from Database	1.1.3	1.1.6	mejora	resuelto
394	08/05/06 08:53	30/01/07 18:42	major	RESOLVED	FIXED	TOL	Decompile a TimeSet expression is not working	1.1.3	1.1.5	fallo	resuelto
395	09/05/06 23:03	10/05/06 09:32	normal	NEW		Tol-Base	EditMaster Problem	1.1.3	1.1.4	fallo	pendiente
396	10/05/06 16:54	06/11/07 10:55	critical	RESOLVED	FIXED	TOL	FormatReal's enhancement: decimal symbol	1.1.3	1.1.6	fallo	resuelto
397	10/05/06 17:03	07/12/06 17:35	normal	RESOLVED	FIXED	TOL	tol.exe crashes when a compound expression is passed by command line using -c	1.1.3	1.1.5	fallo	resuelto
398	11/05/06 23:07	02/12/06 02:28	critical	RESOLVED	FIXED	TOL	B operator malfunctioning	1.1.3	1.1.5	fallo	resuelto
399	24/05/06 18:44	07/11/07 13:01	enhancement	RESOLVED	WONTFIX	TOL	Optional auto-scaling of variables as estimate enhancement	1.1.3	1.1.6	mejora	resuelto
400	26/05/06 10:46	07/12/06 13:04	blocker	RESOLVED	FIXED	TOL	Void cells in bdt's causes bad series reading	1.1.3	1.1.5	fallo	resuelto
401	26/05/06 22:41	07/12/06 13:07	normal	RESOLVED	FIXED	TOL	fail in IncludeBST with 10 fields or more	1.1.3	1.1.5	fallo	resuelto
402	29/05/06 17:09	27/02/07 11:58	normal	RESOLVED	FIXED	Tol-Base	Strange Variable Names in TolBase after executing a BinGroup	1.1.3	1.1.6	fallo	resuelto
403	06/06/06 19:30	28/06/06 17:05	major	RESOLVED	DUPLICATE	TOL	Several problems with F7, F8 and F9	1.1.3	1.1.4	fallo	resuelto
404	07/06/06 11:15	07/12/06 13:12	major	RESOLVED	FIXED	TOL	confusion with the quotes when a Set contains comments	1.1.3	1.1.5	fallo	resuelto
405	08/06/06 20:18	07/12/06 13:15	trivial	RESOLVED	FIXED	TOL	wrong message of error in enclosing columns	1.1.3	1.1.5	fallo	resuelto
406	14/06/06 17:21	07/12/06 13:16	normal	RESOLVED	FIXED	TOL	_DEFAULT_HEADER in BSTFile	1.1.3	1.1.5	fallo	resuelto
407	22/06/06 08:55	30/01/07 18:39	normal	RESOLVED	FIXED	Tol-Base	decompile is not working	1.1.3	1.1.5	fallo	resuelto
408	26/06/06 11:41	02/12/06 02:29	blocker	RESOLVED	FIXED	TOL	A DatCh with W TimeSet makes TOL remain in suspense	1.1.3	1.1.5	fallo	resuelto
409	26/06/06 20:11	02/12/06 02:29	major	RESOLVED	INVALID	TOL	Annoying: PutMatDat does not work inside For...	1.1.3	1.1.5	fallo	resuelto
410	27/06/06 17:12	11/07/06 14:52	normal	NEW		Tol-Base	Find option doesn't work rigth	1.1.3	1.1.4	fallo	pendiente
411	29/06/06 11:58	29/06/06 12:49	minor	RESOLVED	FIXED	Tol-Base	Replce doesn't work in the Eval tab	1.1.3	1.1.4	fallo	resuelto
412	29/06/06 18:41	29/06/06 18:41	major	NEW		Tol-Base	Crash if hit options twice in a graphic	1.1.3	1.1.4	fallo	pendiente
413	01/07/06 11:47	30/01/07 19:08	critical	ASSIGNED		Tol-Base	"unimplemented" message	1.1.3	1.1.5	fallo	pendiente
414	03/07/06 23:27	04/07/06 09:02	minor	RESOLVED	FIXED	Tol-Base	Verifying Syntax	1.1.3	1.1.4	fallo	resuelto
415	05/07/06 16:37	02/12/06 02:29	normal	RESOLVED	FIXED	TOL	sub-hourly timeset's doesn't work	1.1.3	1.1.5	fallo	resuelto
416	05/07/06 18:18	23/10/06 20:26	normal	RESOLVED	INVALID	TOL	Error with IncludeBST	1.1.3	1.1.4	fallo	resuelto
417	12/07/06 15:21	07/12/06 17:35	normal	RESOLVED	FIXED	TOL	segmentation fault	1.1.3	1.1.5	fallo	resuelto
418	17/07/06 10:37	02/12/06 02:30	major	RESOLVED	FIXED	TOL	Errors loading initial TOL file ./initlibrary/_inittol.tol	1.1.3	1.1.5	fallo	resuelto
419	19/07/06 15:17	02/12/06 02:30	minor	RESOLVED	FIXED	TOL	Problem with BinGroup	1.1.3	1.1.5	fallo	resuelto
420	21/07/06 14:35	21/07/06 14:35	enhancement	NEW		Tol-Base	To be able to hide the Tol-Inspector with the Magnifying Glass button.	1.1.3	1.1.4	mejora	pendiente
421	24/07/06 09:06	24/07/06 09:21	blocker	RESOLVED	DUPLICATE	TOL	Problems in _constant.tol	1.1.3	1.1.4	fallo	resuelto
422	25/07/06 15:25	25/07/06 15:25	normal	NEW		Tol-Base	Right button on an named included file doesn`t work	1.1.3	1.1.4	fallo	pendiente
423	08/08/06 11:33	07/12/06 13:22	normal	RESOLVED	FIXED	TOL	Segmentation fault when you using a BDB with a incorrent number fields in Structure argument	1.1.3	1.1.5	fallo	resuelto
424	08/08/06 17:57	02/12/06 02:30	blocker	RESOLVED	FIXED	TOL	Difference between noise in Estimate function and noise calculated with DifEq	1.1.3	1.1.5	fallo	resuelto
425	16/08/06 17:47	02/12/06 02:31	blocker	RESOLVED	FIXED	TOL	Complex vs. Real	1.1.3	1.1.5	fallo	resuelto
426	29/08/06 12:47	02/12/06 02:31	major	RESOLVED	FIXED	TOL	error in CountS	1.1.3	1.1.5	fallo	resuelto
427	29/08/06 13:02	06/11/07 10:58	blocker	RESOLVED	FIXED	TOL	Operations with unknown values don`t return unknown values	1.1.3	1.1.6	fallo	resuelto
428	04/09/06 17:24	02/12/06 02:31	blocker	RESOLVED	FIXED	TOL	Serious problems with MA models	1.1.3	1.1.5	fallo	resuelto
429	12/09/06 16:03	12/09/06 16:03	enhancement	NEW		Tol-Base	Browsing tools for object inspector	1.1.3	1.1.4	mejora	pendiente
430	27/09/06 11:39	02/12/06 02:31	major	RESOLVED	FIXED	TOL	Estimate does not handle unknowns as it used to do	1.1.3	1.1.5	fallo	resuelto
431	29/09/06 16:17	02/12/06 02:32	normal	RESOLVED	FIXED	TOL	Problems with logical functions and unknown values	1.1.3	1.1.5	fallo	resuelto
432	05/10/06 14:52	30/01/07 18:43	blocker	RESOLVED	FIXED	TOL	tol crash after compiling a just decompiled file	1.1.3	1.1.5	fallo	resuelto
433	06/10/06 18:16	02/02/07 13:46	blocker	ASSIGNED		Tol-Base	compile & decompile	1.1.3	1.1.5	fallo	pendiente
434	16/10/06 11:54	02/12/06 02:32	blocker	RESOLVED	FIXED	TOL	segmentation fault when indexing inline the result from IncludeBDT	1.1.3	1.1.5	fallo	resuelto
435	16/10/06 16:51	07/12/06 17:37	blocker	CLOSED	REMIND	TOL	Struct doing weird things...	1.1.3	1.1.5	fallo	postergado
436	18/10/06 13:32	07/11/07 13:02	enhancement	RESOLVED	REMIND	TOL	control de escritura en el log	1.1.3	1.1.6	mejora	postergado
437	19/10/06 12:04	02/12/06 02:32	major	RESOLVED	FIXED	TOL	some objects are not created when evaluating	1.1.3	1.1.5	fallo	resuelto
438	19/10/06 12:50	19/10/06 12:54	minor	RESOLVED	REMIND	TOL	TOL crash reading corrupted BSI files	1.1.3	1.1.4	fallo	postergado
439	19/10/06 16:24	02/12/06 02:32	critical	RESOLVED	FIXED	TOL	Segmentation fault with local structs	1.1.3	1.1.5	fallo	resuelto
440	20/10/06 16:15	06/11/07 10:59	blocker	RESOLVED	INVALID	Tol-Base	MatSerSet does not work in year is less than 1583	1.1.3	1.1.6	fallo	resuelto
441	24/10/06 16:55	02/12/06 02:33	blocker	RESOLVED	FIXED	TOL	Group function doesn't work upper 2^15=32768 elements	1.1.3	1.1.5	fallo	resuelto
442	24/10/06 18:36	02/12/06 02:33	blocker	RESOLVED	FIXED	TOL	BinGroup yields a crash with high number of elements	1.1.3	1.1.5	fallo	resuelto
443	25/10/06 10:46	12/04/07 21:14	enhancement	RESOLVED	FIXED	TOL	Tol/Tolbase binary package	1.1.3	1.1.6	mejora	resuelto
444	06/11/06 16:40	02/12/06 02:33	blocker	RESOLVED	FIXED	TOL	Problems with MatSerSet	1.1.3	1.1.5	fallo	resuelto
445	06/11/06 17:15	02/12/06 02:33	critical	RESOLVED	FIXED	TOL	Errors in addition in matrix	1.1.3	1.1.5	fallo	resuelto
446	06/11/06 17:34	06/11/06 18:14	trivial	ASSIGNED		TOL	Duplicated functions	1.1.3	1.1.4	fallo	pendiente
447	10/11/06 09:14	16/11/06 00:15	enhancement	RESOLVED	FIXED	Tol-Base	Eliminar funcionalidad Ctrl-K sobre el editor	1.1.3	1.1.4	mejora	resuelto
448	14/11/06 18:51	16/11/06 00:18	normal	RESOLVED	FIXED	Tol-Base	Autocorrelación Errónea con "Tabular Autocorrelación"	1.1.3	1.1.4	fallo	resuelto
449	17/11/06 19:11	20/11/06 14:48	major	RESOLVED	FIXED	Tol-Base	Unreadeable .gif figures	1.1.3	1.1.4	fallo	resuelto
450	21/11/06 09:36	07/12/06 13:04	normal	RESOLVED	FIXED	TOL	Include a bdt file make me to do a mistake	1.1.3	1.1.5	fallo	resuelto
451	22/11/06 13:12	02/12/06 02:34	blocker	RESOLVED	FIXED	TOL	Fall of the program executing the AIA function	1.1.3	1.1.5	fallo	resuelto
452	23/11/06 11:07	23/11/06 11:07	enhancement	NEW		Tol-Base	Save just when needed	1.1.3	1.1.4	mejora	pendiente
453	29/11/06 18:47	07/12/06 17:38	blocker	RESOLVED	FIXED	TOL	command line -c	1.1.3	1.1.5	fallo	resuelto
454	01/12/06 12:22	02/12/06 02:34	minor	RESOLVED	FIXED	TOL	Mysterious error message	1.1.4	1.1.5	fallo	resuelto
455	04/12/06 10:55	04/12/06 18:37	blocker	RESOLVED	FIXED	TOL	DBTable falls	1.1.4	1.1.5	fallo	resuelto
456	04/12/06 10:58	04/12/06 11:37	blocker	RESOLVED	FIXED	TOL	Series return of Estimate	1.1.4	1.1.5	fallo	resuelto
457	05/12/06 12:27	05/12/06 17:46	blocker	RESOLVED	FIXED	TOL	a 'DatCh' to 'SerTms' timeset makes TOL crash	1.1.4	1.1.5	fallo	resuelto
458	10/12/06 19:41	20/02/07 10:44	major	RESOLVED	FIXED	TOL	fail to resolve overloaded built-in operator	1.1.4	1.1.6	fallo	resuelto
459	17/12/06 11:51	18/12/06 18:43	critical	RESOLVED	FIXED	Tol-Base	erasure of rows in btable.tcl	1.1.4	1.1.5	fallo	resuelto
460	17/12/06 11:51	27/02/07 13:06	major	NEW		Tol-Base	problem after occulting a series line	1.1.4	1.1.6	fallo	pendiente
461	17/01/07 11:25	30/01/07 16:28	major	NEW		TOL	WinRmtProcessAlive fails	1.1.4	1.1.5	fallo	pendiente
462	24/01/07 11:37	19/02/07 17:37	blocker	RESOLVED	FIXED	TOL	Problems with Show	1.1.4	1.1.5	fallo	resuelto
463	29/01/07 13:19	03/02/07 00:34	blocker	ASSIGNED		TOL	Problemas DBOpen	1.1.4	1.1.5	fallo	pendiente
464	30/01/07 18:10	31/01/07 11:34	critical	RESOLVED	FIXED	TOL	EvalArgs fails	1.1.4	1.1.5	fallo	resuelto
465	02/02/07 18:32	02/02/07 18:32	enhancement	NEW		Tol-Base	some proposals of improvements for tables	1.1.4	1.1.5	mejora	pendiente
466	02/02/07 19:03	02/02/07 19:03	enhancement	NEW		Tol-Base	some proposals of improvements for graphics	1.1.4	1.1.5	mejora	pendiente
467	07/02/07 11:31	08/02/07 13:01	critical	RESOLVED	FIXED	TOL	Ois.Store data loss	1.1.4	1.1.5	fallo	resuelto
468	09/02/07 10:31	19/02/07 19:50	blocker	RESOLVED	FIXED	TOL	WriteLn	1.1.4	1.1.5	fallo	resuelto
469	14/02/07 12:48	15/02/07 20:33	blocker	RESOLVED	FIXED	TOL	GSL solving on matrices with empty dimensions	1.1.4	1.1.5	fallo	resuelto
470	16/02/07 11:24	16/03/07 11:01	blocker	RESOLVED	FIXED	Tol-Base	order of decompile matters	1.1.4	1.1.6	fallo	resuelto
471	19/02/07 13:34	19/02/07 17:16	major	RESOLVED	FIXED	TOL	Suma de TimeSet sin nombre	1.1.4	1.1.5	fallo	resuelto
472	19/02/07 16:15	19/02/07 17:23	major	RESOLVED	INVALID	TOL	DatCh doesn´t work right	1.1.4	1.1.5	fallo	resuelto
473	26/02/07 14:14	26/02/07 18:54	blocker	ASSIGNED		Tol-Base	error in edTableGeneric component	1.1.5	1.1.6	fallo	pendiente
474	27/02/07 11:44	27/02/07 12:51	trivial	NEW		Tol-Base	Splash decides not to die	1.1.5	1.1.6	fallo	pendiente
475	28/02/07 17:31	01/03/07 00:20	blocker	RESOLVED	FIXED	Tol-Base	problema en ACF	1.1.5	1.1.6	fallo	resuelto
476	02/03/07 15:48	02/03/07 16:35	blocker	RESOLVED	FIXED	TOL	Command involving Serie and TimeSet crashes TOL	1.1.5	1.1.6	fallo	resuelto
477	09/03/07 12:44	09/03/07 12:44	minor	NEW		Tol-Base	Graphics	1.1.5	1.1.6	fallo	pendiente
478	12/03/07 16:00	06/11/07 11:01	blocker	RESOLVED	FIXED	TOL	Real 1/0 = 1/0 returns ?	1.1.5	1.1.6	fallo	resuelto
479	13/03/07 11:13	14/03/07 20:49	critical	RESOLVED	FIXED	TOL	text expression fail when used as Set index	1.1.5	1.1.6	fallo	resuelto
480	14/03/07 12:26	15/03/07 10:50	major	RESOLVED	FIXED	TOL	Wrong behaviour of some logic functions involving unknown values	1.1.5	1.1.6	fallo	resuelto
481	15/03/07 10:53	16/03/07 11:05	normal	RESOLVED	FIXED	TOL	Reassignation (:=) of a set element fails	1.1.5	1.1.6	fallo	resuelto
482	15/03/07 11:01	16/03/07 11:01	blocker	RESOLVED	DUPLICATE	TOL	Decompilation weirdness	1.1.5	1.1.6	fallo	resuelto
483	20/03/07 22:37	21/03/07 16:40	blocker	RESOLVED	FIXED	Tol-Base	decompiling self references created with :=	1.1.5	1.1.6	fallo	resuelto
484	10/04/07 15:39	07/11/07 13:17	normal	RESOLVED	FIXED	TOL	BDT File needs to finish with an empty line	1.1.5	1.1.6	fallo	resuelto
485	04/05/07 18:35	07/11/07 21:01	normal	RESOLVED	FIXED	TOL	DBSeries makes the series global	1.1.5	1.1.6	fallo	resuelto
486	17/05/07 09:15	17/05/07 09:20	blocker	RESOLVED	INVALID	TOL	DifEq does not work well	1.1.5	1.1.6	fallo	resuelto
487	17/05/07 18:23	21/05/07 12:01	blocker	ASSIGNED		Tol-Base	Graph special set	1.1.5	1.1.6	fallo	pendiente
488	18/05/07 12:25	18/05/07 18:13	major	RESOLVED	FIXED	TOL	error message in estimation function	1.1.5	1.1.6	fallo	resuelto
489	28/05/07 11:18	28/05/07 11:18	enhancement	NEW		Tol-Base	auto-save-recover	1.1.5	1.1.6	mejora	pendiente
490	28/05/07 11:47	07/11/07 13:11	enhancement	RESOLVED	REMIND	TOL	Solving fields indentification in parsing time	1.1.5	1.1.6	mejora	postergado
491	31/05/07 15:43	31/05/07 15:50	normal	RESOLVED	REMIND	TOL	Simply definition of a column matrix returns a row matrix	1.1.5	1.1.6	fallo	postergado
492	05/06/07 09:50	05/06/07 10:15	normal	RESOLVED	WORKSFORME	Tol-DBD	Vars DBA,DBExec and DBWriteTime doesn't exists	1.1.5	1.1.6	fallo	resuelto
493	06/06/07 13:00	07/06/07 11:04	normal	RESOLVED	FIXED	TOL	Bimonthly and Bimensual TimeSet definition	1.1.5	1.1.6	fallo	resuelto
494	06/06/07 13:00	06/06/07 14:13	normal	RESOLVED	DUPLICATE	TOL	Bimonthly and Bimensual TimeSet definition	1.1.5	1.1.6	fallo	resuelto
495	06/06/07 13:01	06/06/07 14:13	normal	RESOLVED	DUPLICATE	TOL	Bimonthly and Bimensual TimeSet definition	1.1.5	1.1.6	fallo	resuelto
496	20/06/07 15:09	07/11/07 15:08	blocker	RESOLVED	FIXED	TOL	Tol shutdown when editing inputs from inputs tree	1.1.5	1.1.6	fallo	resuelto
497	01/07/07 01:30	01/07/07 13:42	critical	RESOLVED	FIXED	TOL	SubRow breaks down TOLBase	1.1.5	1.1.6	fallo	resuelto
498	01/07/07 23:00	02/07/07 18:59	critical	RESOLVED	FIXED	TOL	Problems with variables asociates to e	1.1.5	1.1.6	fallo	resuelto
499	10/07/07 11:51	06/11/07 11:04	critical	RESOLVED	FIXED	Tol-Base	Mistake in OIS	1.1.5	1.1.6	fallo	resuelto
500	13/07/07 14:18	16/07/07 16:30	major	RESOLVED	FIXED	Tol-Base	unable to change graph options after including ois set	1.1.5	1.1.6	fallo	resuelto
501	31/07/07 11:29	31/07/07 12:42	critical	RESOLVED	FIXED	TOL	TOL crashes when L is a 0x0 matrix in RandTruncatedMultNormal	1.1.5	1.1.6	fallo	resuelto
502	03/08/07 09:12	27/08/07 23:25	enhancement	RESOLVED	FIXED	TOL	PutDateFormat functions doesn't works	1.1.5	1.1.6	mejora	resuelto
503	27/08/07 00:14	28/08/07 02:03	critical	RESOLVED	FIXED	TOL	Kernel function makes TOL to crash	1.1.5	1.1.6	fallo	resuelto
504	28/08/07 13:30	28/08/07 18:17	normal	RESOLVED	FIXED	TOL	Methods() function	1.1.5	1.1.6	fallo	resuelto
505	28/08/07 13:45	28/08/07 18:18	critical	RESOLVED	FIXED	TOL	Median() function and the unknown real number	1.1.5	1.1.6	fallo	resuelto
506	02/09/07 20:31	05/09/07 13:05	blocker	RESOLVED	FIXED	TOL	tol crash in constrained multinormal generation with an ill-conditioned covariance matrix	1.1.5	1.1.6	fallo	resuelto
507	04/09/07 14:00	05/09/07 13:05	blocker	RESOLVED	FIXED	TOL	GibbsConstrainedMNormal fails when using SVD	1.1.5	1.1.6	fallo	resuelto
508	14/09/07 12:49	14/09/07 13:36	normal	ASSIGNED		TOL	Iterations number report	1.1.5	1.1.6	fallo	pendiente
509	27/09/07 10:01	27/09/07 10:01	major	NEW		Tol-Base	Log reload on Object Inspector -> Output	1.1.5	1.1.6	fallo	pendiente
510	27/09/07 10:21	27/09/07 10:21	major	NEW		Tol-Base	See "Object" Definition	1.1.5	1.1.6	fallo	pendiente
511	28/09/07 11:34	28/09/07 20:46	critical	RESOLVED	FIXED	TOL	Include makes TOL to break down	1.1.5	1.1.6	fallo	resuelto
512	01/10/07 13:15	06/11/07 10:40	enhancement	RESOLVED	FIXED	TOL	Description of GibbsConstrainedMNormal	1.1.5	1.1.6	mejora	resuelto
513	01/10/07 14:41	01/10/07 14:55	enhancement	ASSIGNED		TOL	New function about LDLt transformation	1.1.5	1.1.6	mejora	pendiente
514	02/10/07 19:21	25/10/07 15:17	major	RESOLVED	FIXED	TOL	RandConstrainedMNormal crashes Tol Base	1.1.5	1.1.6	fallo	resuelto
515	08/10/07 15:01	09/10/07 19:32	enhancement	RESOLVED	FIXED	TOL	New funcion Append in Set	1.1.5	1.1.6	mejora	resuelto
516	09/10/07 11:42	09/10/07 20:22	blocker	RESOLVED	LATER	Tol-Base	TolBase 1.1.5 Installation	1.1.5	1.1.6	fallo	postergado
517	29/10/07 11:31	06/11/07 16:27	normal	RESOLVED	FIXED	Tol-Doc	missing function descrption	1.1.5	1.1.6	fallo	resuelto
518	30/10/07 09:45	30/10/07 10:46	enhancement	ASSIGNED		Tol-Base	hold on functionality for graphics	1.1.5	1.1.6	mejora	pendiente
519	02/11/07 11:32	02/11/07 14:59	normal	NEW		Tol-Base	error when pussing the statistics button in a series chart	1.1.5	1.1.6	fallo	pendiente

## Versiones
Version	Release date	Development days
1.1.0	2003-01-01		37622
1.1.1	2004-04-05	329	38082	SI(B2<=38082;"1.1.0";	SI(B2<=38082;"1.1.0";
1.1.2	2005-04-22	273	38464	SI(B2<=38464;"1.1.1";
1.1.3	2006-03-20	237	38796	SI(B2<=38796;"1.1.2";
1.1.4	2006-11-30	182	39051	SI(B2<=39051;"1.1.3";
1.1.5	2007-02-20	59	39133	SI(B2<=39133;"1.1.4";
1.1.6	2007-11-20	195	39406	SI(B2<=39406;"1.1.5";